## Cover
HANOI UNIVERSITY OF SCIENCE AND TECHNOLOGY
School of Information and communications technology
Test Plan
Version 1.0
AIMS
Subject: ITSS
GROUP 19
Dương Quang Trí - 20215248 Nguyễn Viết Thuận - 20210826
Trịnh Thị Diệu Thùy - 20215247
Nguyễn Chí Trung - 20200643
Hanoi, 6, 2024

## Table of Contents
Table of Contents
1 | Instructions
2 | Overall Description
3 | Testing Approach Strategy
4 | Unit Testing Summary
5 | Test Case Details

## Introduction
1. Introduction
1.1. Objective
This Test Plan outlines the testing strategy for the e-commerce desktop application, covering all test functions including unit, integration, system, and user acceptance testing. It is intended for project managers, QA managers, test engineers, developers, product owners, and stakeholders. The plan ensures the application meets its requirements and includes security and privacy considerations to protect user data and comply with data protection regulations.
1.2 Scope
Our application provides users with desktop e-commerce software. Due to the requirement, we provide view, select and place order goods for users and management about goods and orders for admin. We also provide a friendly-user interface for high experience.
1.3. Glossary
Term (mấy từ viết tắt) | Explain
ITSS | Information Technology Systems and Services
RAM | Random Access Memory
IDE | Integrated Development Environment
JRE | Java Runtime Environment
1.4. References
[1] Centers for Medicare & Medicaid Services, "System Design Document Template," [Online]. Available: https://www.cms.gov/Research-Statistics-Data-and-Systems/CMS-Information-Technology/XLC/Downloads/SystemDesignDocument.docx.

## Overall Description
2. Overall Description
2.1. General Overview
The Software Requirements Document is divided into 6 sections with various subsections. The two first sections are the introduction and the general overview of the AIMS project. The third section is the detail requirements where we provide the various types of dỉagram and its specifications. The fourth section is System architecture and architecture design. In this part, we describe the architecture which we choose to develop the software and some information about it. The detailed design of the architecture is also in this section. The fifth section is the detailed design part which contains the interface design, class design and so on. The last section is the design consideration in which we appreciate the design pattern, design concept, ...
2.2. Assumptions/Constraints/Risks
2.2.1. Assumptions
Users of the software should have a stable Internet connection. Additionally, because our program is a desktop application, the user also needs a laptop or desktop computer with an operating system (we recommend 64-Bit Microsoft Windows 10 or later, macOS 10.13 or later, or any Linux distribution that allows running applications) in order to utilize the apps. Regarding the system requirements, we would say that you need at least 2 GB of RAM and a solid-state drive with at least 3 GB of free space. The most recent version of JRE is also required, and a screen resolution of 1280 x 800 is advised.
2.2.2. Constraints
Hardware or Software Environment Constraint: The application must be compatible with Windows, macOS, and Linux operating systems. Impact: This requires cross-platform development tools and libraries, which may limit the choice of programming languages and frameworks. End-User Environment Constraint: The application should be user-friendly and require only basic PC skills. Impact: The user interface must be intuitive, with clear instructions and simple navigation. This will involve extensive usability testing and potentially a simplified design to ensure accessibility for all users.
2.2.3. Risks
Developing desktop e-commerce software involves several risks, including compatibility issues across operating systems, ensuring a user-friendly interface for those with basic PC skills, and managing limited development resources. Compliance with industry standards and integrating with third-party services are essential to avoid legal and operational issues.

## Testing Approach Strategy
3. Testing Approach/Strategy
< Describe the overall approach that will be used to test all functions, features, and requirements of the automated system, application, or situation for which the Test Plan applies. As applicable to this Test Plan, describe the measures to be taken to ensure all aspects of the system are successfully tested and can be implemented. Document key aspects of the testing approach, such as content, methodology, prioritization, and progression of development, validation, implementation, and operational testing activities to be performed during the corresponding lifecycle phases For example, will some unit and application integration testing be done, and then some more development, and so on? Is a prototype being built that will be usability tested before the releasable software is developed? Also include plans for testing related documentation (e.g., installation instructions, User Manual, Operations & Maintenance (O&M) Manual, Training Artifacts, etc.) and for conducting applicable readiness reviews. Also, if applicable, describe how reuse will be applied to the testing effort to make testing more efficient and less costly.>

## Unit Testing Summary
4. Unit Testing Summary
4.1. Traceability from Test Cases to Use Cases
<Mark the cell with an "x" where the Test Case tests.>
USE CASE ID |  |  | UC001 | UC002 | UC003 | UC004 | UC005 | UC006 | UC007 | UC008 | Main usecase is Place order(001), Place rush order(002), Pay order(003), Add to cart (004), Search media(005)
Test Case ID | Test CaseTitle | Totals | bar: UC001 to UC008
TC001 | Place order | 1 | bar: UC001
TC002 | Place rush order | 1 | bar: UC002
TC003 | Pay order | 1 | bar: UC003
TC004 | Add to cart | 1 | bar: UC004
TC005 | Search media | 1 | bar: UC005
Table: Test Case-to-Use Case Traceability Matrix
4.1.1. Test Suite for UC002-"Use Case Name"
Test Suite ID | Test Suite Title | Description | UC003: Test Cases
TS001 | Place order | Place order all items on cart | UC003: TC001; UC004: TC001
TS002 | Place rush order | Place order all items on cart with rush delivery | UC003: TC002; UC004: TC002
TS003 | Pay order | Pay for your order | UC003: TC003; UC004: TC003
TS004 | Add to cart | Add an item to your cart | UC003: TC004; UC004: TC004
TS005 | Search media | Search media by entering words | UC003: TC005; UC004: TC005
4.2. Traceability from Test Cases to Requirements
<Mark the cell with an "x" where the Test Case tests.>
REQUIREMENT ID |  |  | RQ001 | RQ002 | RQ003 | RQ004 | RQ005 | RQ006 | RQ007 | RQ008 | Main requirement functionality is Place order function(001), Place rush order function(002), Pay order function(003), Add to cart function (004), Search media function(005)
Test Case ID | Test CaseTitle | Totals | bar: RQ001 to RQ008
TC001 | Place order | 1 | bar: RQ001
TC002 | Place rush order | 1 | bar: RQ002
TC003 | Pay order | 1 | bar: RQ003
TC004 | Add to cart | 1 | bar: RQ004
TC005 | Search media | 1 | bar: RQ005
4.2.1. Test Suite for RQ001-"Requirement Title"
Test Suite ID | Test Suite Title | Description | RQ003: Test Cases
TS001 | Place order | Place order all items on cart | RQ003: TC001; RQ004: TC001
TS002 | Place rush order | Place order all items on cart with rush delivery | RQ003: TC002; RQ004: TC002
TS003 | Pay order | Pay for your order | RQ003: TC003; RQ004: TC003
TS004 | Add to cart | Add an item to your cart | RQ003: TC004; RQ004: TC004
TS005 | Search media | Search media by entering words | RQ003: TC005; RQ004: TC005

## Test Case Details
5. Test Case Details
5.1. Test Case Specification for "Place order"
Test Case ID |  | TC001 | Test Case Description | Test the place order usecase
Created By |  | Nguyễn Cảnh Phước | Reviewed By | Nguyễn Cảnh Phước | Version | 1.0
QA Tester’s Log |  | Review comments from Reviewer incorprate in version 1.0
Tester's Name |  | Nguyễn Cảnh Phước | Date Tested | 04/01/2025 | Test Case (Pass/Fail/Not Executed) | Pass
# | Prerequisites:
1 | Cart has at least one item
# | Test Data |  | Value
1 | name |  | Nguyen Van A
2 | phone |  | 123123123
3 | province |  | Ha Noi
4 | address |  | hanoi
5 | email |  | nguyenvana@gmail.com
Test Scenario |  | Place order while cart has at least one item
Step # | Step Details |  | Expected Results | Actual Results | Pass / Fail / Not executed / Suspended
1 | Click to cart button |  | System show all item in cart | As Expected | Pass
2 | Click Plac order button |  | System show delivery form | As Expected | Pass
3 | Input needed information |  | Cutomer is logged in | As Expected | Pass
4 | Click confirm |  | System show payment method options | As Expected | Pass
5.2. Test Case Specification for "Place rush order"
Test Case ID |  | TC002 | Test Case Description | Test place rush order usecase
Created By |  | Giang Trung Quân | Reviewed By | Giang Trung Quân | Version | 1.0
QA Tester’s Log |  | Review comments from Reviewer incorprate in version 1.0
Tester's Name |  | Giang Trung Quân | Date Tested | 04/01/2025 | Test Case (Pass/Fail/Not Executed) | Pass
# | Prerequisites:
1 | Cart has at least one item
# | Test Data |  | Value
1 | name |  | Nguyen Van A
2 | phone |  | 123123123
3 | province |  | Ha Noi
4 | address |  | hanoi
5 | email |  | nguyenvana@gmail.com
Test Scenario |  | Place order while cart has at least one item
Step # | Step Details |  | Expected Results | Actual Results | Pass / Fail / Not executed / Suspended
1 | Click to cart button |  | System show all item in cart | As Expected | Pass
2 | Click Plac order button |  | System show delivery form | As Expected | Pass
3 | Input needed information |  | Cutomer is logged in | As Expected | Pass
4 | Click rush order checkbox |  | System show checkbox is checked | As Expected | Pass
5 | Click confirm |  | System show rush order | As Expected | Pass
6 | Choose delivery time |  | System show choosed rush order | As Expected | Pass
6 | Enter delivery instruction |  | System show your input | As Expected | Pass
7 | Click confirm |  | System show payment method options | As Expected | Pass
5.3. Test Case Specification for "Pay order"
Test Case ID |  | TC003 | Test Case Description | Test pay order usecase
Created By |  | Bùi Trung Quân | Reviewed By | Bùi Trung Quân | Version | 1.0
QA Tester’s Log |  | Review comments from Reviewer incorprate in version 1.0
Tester's Name |  | Bùi Trung Quân | Date Tested | 04/01/2025 | Test Case | Pass
# | Prerequisites:
1 | You confirm order
# | Test Data |  | Value
1 | bank |  | NCB
2 | card series |  | 9123912391292
3 | name |  | Nguyen Van A
4 | start date |  | 7/15
5 | otp password |  | 123456
Test Scenario |  | After confirm place order/place rush order
Step # | Step Details |  | Expected Results | Actual Results | Pass / Fail / Not executed / Suspended
1 | Click confirm payment |  | System show bank list | As Expected | Pass
2 | Choose a bank |  | System show payment infor form | As Expected | Pass
3 | Input needed information |  | System show your input information | As Expected | Pass
4 | Click continue button |  | System show confirm notification | As Expected | Pass
5 | Click agree and continue button |  | System require otp password | As Expected | Pass
6 | Input otp password and click pay button |  | System show payment status | As Expected | Pass
5.4. Test Case Specification for "Add to cart"
Test Case ID |  | TC004 | Test Case Description | Test add to cart usecase
Created By |  | Nguyễn Minh Phương | Reviewed By | Nguyễn Minh Phương | Version | 1.0
QA Tester’s Log |  | Review comments from Reviewer incorprate in version 1.0
Tester's Name |  | Nguyễn Minh Phương | Date Tested | 04/01/2025 | Test Case | Pass
# | Prerequisites:
1 | None
# | Test Data |  | Value
Test Scenario |  | User at home screen
Step # | Step Details |  | Expected Results | Actual Results | Pass / Fail / Not executed / Suspended
1 | Choose number of media which you want |  | System show number of copies | As Expected | Pass
2 | Click add to cart |  | System show notification: "media is added to cart" | As Expected | Pass
5.5. Test Case Specification for "Search media"
Test Case ID |  | TC005 | Test Case Description | Test search media usecase
Created By |  | Vũ Việt Phương | Reviewed By | Vũ Việt Phương | Version | 1.0
QA Tester’s Log |  | Review comments from Reviewer incorprate in version 1.0
Tester's Name |  | Vũ Việt Phương | Date Tested | 04/01/2025 | Test Case | Pass
# | Prerequisites:
1 | None
# | Test Data |  | Value
Test Scenario |  | User at home screen
Step # | Step Details |  | Expected Results | Actual Results | Pass / Fail / Not executed / Suspended
1 | Input word to search |  | System shows input word | As Expected | Pass
2 | Click search button |  | System show matched media | As Expected | Pass